## BrainStorming Sheet
User Stories | Priority | Notes | Questions for Karen | Priority
As a parent I want to be able to view the sign up sheet easily so that I will be able to select which dates I want to come in. | 1 |  | We might be missing some features that we have not thought of, which key features for each group do you think would be essential? | 1
As a parent I want to be able to view my historical hours so that I will know if I can donate my extra hour | 55 |  | Regarding donating hours. Can they only donate hours from the current week before the reset or is there a bank of hours from previous? | 2
As a parent I want to be able to view how many hours that I have facilitated this week so that I know if I have met my quota. | 6 |  | Should all members have add/edit/delete options? | 3
As a parent I want to be able to remove my name from a sign up so that if I made a mistake I can correct it. | 4 |  | Do you want passwords for each user? Or rely on honesty? | 4
As a parent I want to be able to remove family members so that they are no longer part of the group. |  |  | will there be a database of names provided or will the users create their accounts themselves | 5
As a parent I want to be able to view the weeks in advance so that I can plan out my schedule. | 10 |  | As a parent, I want to check in/check out for my scheduled times **parents or teachers have this power??? | 6
As a parent I want to be able to book time off facilitation so that we can go on vacation. | 50 | Vacation forms can excempt this | Should there be a family account for the parents and other or seperate accounts for each? | 7
As a parent I want to be able to edit my entry in the schedule when I make a mistake. | 5 |  | What happens if there is a holiday during the week and there are not enough hours for everyone? | 8
As a parent I want to be able to change my last name in the system when I get I get married/ a divorce. | 80 |  | Who should be admins? | 9
As a parent I want to be able to see the schedule up until a month from today | 40 |  | How many months in advance/in the past can parents see? Can the admin see? etc. | 10
As a parent, I want to add/edit members in my family account | 10 |  | Should account creation be limited to public for creation of board member, teacher, and admin accounts? Or rely on honesty? | 11
As a parent, I want to donate extra hours to other family accounts | 3 |  | What would you prefer user account to be assigned as? (e.g. Family345987, just a number, etc). | 12
As a parent, I want to see how many are required to complete weekly | 2 |  | What are the most important features that differs the board members from admin? | 13
As a parent, I want to have a forget username/password option | 85 |  | is there a maximum number of hours i can donate? Can you donate your minimum hours for the week if necessary? | 14
As a parent, I want to sign up for field trips | 100 |  | What are the most important features that differs the board members from admin? | 15
As a parent, I want to check in/check out for my scheduled times **parents or teachers have this power??? | 90 |  | Single admin system vs board of directors and/or others having admin permissions | 16
As a parent, I want to cancel my registration | 70 |  | On note that not all faciliators are parents, do admin and boardmembers want to facilitate too? | 17
As a parent, I want to sign up for morning/lunch/afternoon
As a parent, I want to notify that my family is on vacation
As a parent, I want to notify that I am on maternity leave
As a parent, I want to notify that I will be exempt from facilitation hours |  |  | Things that Karen liked:
As a parent, I want to see a report of family historical data | 65 |  | ***Karen like the idea of checking in and checking out
***Wants Admin to have alot of control
karen@themommanager.com
***need documentation for group work, folder for mock ups
As a teacher I want to be able to filter the facilitators by classroom so I know who will be coming in today. | 7
As a teacher I want to be able to see which facilitator is signed up per time slot so I know who to contact in case anything comes up or changes. | 15
As a teacher I want to be able to see the history/statistics of facilitators in my classroom so in case of an emergency and I will have a contact list.
As a teacher I want to see statistics for individual classrooms
As a teacher I want to view the facilitation schedule for the day
As a teacher I want ot create field trip forms
As a teacher I want to create weekly signups schedules
As a teacher I want to see the check in/check out statistics
As a teacher I want to see the sign up/cancellation statistics
As a teacher I was to view the facilitation schedule for the month
As an admin I want to be able to approve/deny requests for facilitation exemption
As admin I want to be able to add/delete accounts/users so I can clean up the system when someone graduates. | 1
As admin I want to be able to view history/statistics of facilitators so I can gauge how well the volunteer is going.
As admin I want to be able to sign up/remove/move facilitator sign up so I can combat abuse of the system if that happens.
As admin i want to edit hours
As admin i want to reset passwords
i want to notify people for important dates/insufficient hours etc
i want to check who is checked in/checked out
i want to track total hours by week/month
i want to create sign up sheets/weekly schedules

## Testing
Test
Automated testing for database. Automated making database and testing if proper tables. | Majority of UI test was done manually
Program to insert admin account if that does not exist
Manual testing for login. Type into known accounts and see if accept login. Type false info and see if reject. Test if login redirects to proper page.
Manual Testing for html pages. Making sure all pages link to the proper one.
Print functions for testing if passing data from html to html worked. Same for flask testing. Used a lot of print functions.
Manual testing for the flash messages. Test to see if they show up.
Manual testing done for statistics. Insert test data and see if actually mapped.
Manually inserted test data into tables to see if everything worked together
Some automated DB functions to return false if failed.
Tested on multiple browsers but found only firefox worked correctly
Bugs
Removing user account should also remove the shifts they have
Changing name of facilitator should also affect the shifts they are doing

## Moqups
https://app.moqups.com/hanjouraa/ZIEbgJLctA/view

## Sprint 1
User Stories |  |  | Goals
As admin I want to be able to add/delete accounts/users so I can clean up the system when someone graduates. | 3 |  | Front end
As admin I want to be able to sign up/remove/move facilitator sign up so I can combat abuse of the system if that happens. | 2 |  | Back end
i want to create sign up sheets/weekly schedules | 5 |  | Login Screen
As admin I want to be able to create accounts for all the users | 2 |  | Working Database
As admin I want a specific page just for me | 1 |  | Light scheduling implementation
As teacher I want a specific page just for me | 1
As family I want a specific page just for me | 1
As board member I want a specific page just for me | 1
As user I want to be able to login with a username and password | 3
Login screen for all users | 2
As admin I want to be able to view all the accounts in the system | 4
Tech Stories
Learn HTML | 2
Learn CSS | 2
Learn JS | 2
Learn Flask Python | 2
Learn connectivity | 2
Working database | 2
| Available Days | (3 week sprint)
Matthew | 9
Ahmad | 9
Lukas | 9
Raymond | 9
36 available man-days

## Sprint 2018-01-28
User Stories |  | Done
As admin I want to be able to add/delete accounts/users so I can clean up the system when someone graduates. | 3 | As admin I want a specific page just for me | 1
As admin I want to be able to sign up/remove/move facilitator sign up so I can combat abuse of the system if that happens. | 2 | As teacher I want a specific page just for me | 1
i want to create sign up sheets/weekly schedules | 5 | As family I want a specific page just for me | 1
As admin I want to be able to create accounts for all the users | 2 | As board member I want a specific page just for me | 1
As user I want to be able to login with a username and password | 3 | Learn HTML | 2
Login screen for all users | 2 | Learn CSS | 2
As admin I want to be able to view all the accounts in the system | 4
Tech Stories
Learn JS | 2
Learn Flask Python | 2
Learn connectivity | 2
Working database | 2
Available Days
|  | Matthew | 9
|  | Ahmad | 9
|  | Lukas | 9
|  | Raymond | 9 | (3 week sprint)
36 available man-days

## Sprint 2018-02-04
User Stories |  | Done
As admin I want to be able to add/delete accounts/users so I can clean up the system when someone graduates. | 3 | Login screen for all users | 2
As admin I want to be able to sign up/remove/move facilitator sign up so I can combat abuse of the system if that happens. | 2 | Learn JS | 2
i want to create sign up sheets/weekly schedules | 5 | Learn Flask Python | 2
As admin I want to be able to create accounts for all the users | 2 | Learn connectivity | 2
As user I want to be able to login with a username and password | 3 | Working database | 2
As admin I want to be able to view all the accounts in the system | 4
Available Days
|  | Matthew | 9
|  | Ahmad | 9
|  | Lukas | 9
|  | Raymond | 9 | (3 week sprint)
36 available man-days

## Sprint 2018-02-11
User Stories |  | Done
As admin I want to be able to sign up/remove/move facilitator sign up so I can combat abuse of the system if that happens. | 2 | As admin I want to be able to create accounts for all the users | 2
i want to create sign up sheets/weekly schedules | 5 | As user I want to be able to login with a username and password | 3
|  | As admin I want to be able to view all the accounts in the system | 4
|  | As admin I want to be able to add/delete accounts/users so I can clean up the system when someone graduates. | 3
Available Days
|  | Matthew | 9
|  | Ahmad | 9
|  | Lukas | 9
|  | Raymond | 9 | (3 week sprint)
36 available man-days

## Sprint 1 Burndown chart
| Week0 | Week1 | Week2 | Week3
Actual Remaining Hours | 37 | 29 | 19 | 7
Estimated Remaining Hours | 37 | 24.67 | 12.34 | 0

## Spring 1 Retrospective
Retrospective
Good
Got a lot of manhours in
Successfully integrated the front end and back end
Met our preset goals
Got over a lot of integration hiccups
Not so Good
Didn’t estimate how long it would take to learn a new technology and implement it
We should define our user stories more descriptively
Hard to adjust to sprint and do organized documentation for all group members
Overestimated our goals, did not finish sprint
Improvement
Better documentation, more descriptive
More organized documentation
Estimate our goals better

## Sprint 2
User Stories | Story Points |  |  | Goals
As an Admin I want to be able to add facilitators to the family class | 2 |  |  | Features for Admin:
As an Admin I want to be able to delete facilitators from the family class | 1 |  |  | Adding, Removing, Deleting faciliator
As an Admin I want to be able to view the stats of the facilitatoring hours, weekly, month, yearly | 7 |  |  | Adding, Removing, Deleting child
As Admin I want to be able to edit the scheudule for all color rooms | 7 |  |  | Adding, Removing, Deleting from schedule
As Board I want to be able to view the schedule | 1 |  |  | View yearly stats
As Board I want to be able to view the stats for facilitating hours, weekly, month, yearly | 1 | (same implementation as admin) |  | Features for Board:
As Teacher I want to be able to view schedule from all color rooms | 1 |  |  | Viewing the schedule
As family I want to be able to edit my own schedule, delete or add. But only my accounts | 2 |  |  | Viewing the yearly stats
As Family I want to be able to view how many hours I need to facilitate for. | 2 |  |  | Features for Teacher:
As a general user, I want my info to be secure. | 2 | (need to do tech story for encryption first) |  | Viewing the Schedule
As a general user I want to be able to identify who is faciliatating for a shift. | 1 |  |  | Feature for family:
As a general user I want to be able to see calendar display | 2 |  |  | Viewing the schedule
add remove or delete their own shifts
view how many hours have to volunteer
Tech Stores:
Find, Learn, Test calendar framework | 4
Find, Learn, Test encryption for password | 7
Find, Learn, Test Graphing framework | 4
Red is taken out to fit the allotted Story Points (36)
Total | 36
| Available Days | (4 week sprint)
Matthew | 9
Ahmad | 11
Lukas | 9
Raymond | 9
38 available man-days
Last Sprint's Focus Factor: 35 Story Points/ 36 man days = 0.97%
Focus Factor: 0.97%
This sprint's estimated velocity: 38 man days * 0.97 = 36 story points

## Sprint 2018-02-18
User Stories | Story Points | Done
As Admin I want to be able to edit the scheudule for all color rooms | 7 | As an Admin I want to be able to add facilitators to the family class | 2
As Board I want to be able to view the schedule | 1 | As an Admin I want to be able to delete facilitators from the family class | 1
As Teacher I want to be able to view schedule from all color rooms | 1
As family I want to be able to edit my own schedule, delete or add. But only my accounts | 2 | Slow week for other school work catch up. Did some light work on functionality that was not 100% completed from last sprint
As Family I want to be able to view how many hours I need to facilitate for. | 2
As a general user, I want my info to be secure. | 2
As a general user I want to be able to identify who is faciliatating for a shift. | 1
As a general user I want to be able to see calendar display | 2
Tech Stores:
Find, Learn, Test calendar framework | 4
Find, Learn, Test encryption for password | 7
Find, Learn, Test Graphing framework | 4

## Sprint 2018-02-25
User Stories | Story Points | Done
As Admin I want to be able to edit the scheudule for all color rooms | 7 | Find, Learn, Test calendar framework | 4
As Board I want to be able to view the schedule | 1 | As a general user I want to be able to see calendar display | 2
As Teacher I want to be able to view schedule from all color rooms | 1
As family I want to be able to edit my own schedule, delete or add. But only my accounts | 2
As Family I want to be able to view how many hours I need to facilitate for. | 2
As a general user, I want my info to be secure. | 2 | Slow week because learning calendar framework took a lot more time than 4 man days
As a general user I want to be able to identify who is faciliatating for a shift. | 1 | Tested multiple frameworks, high calendar, daypilot, kalandae
Due to time pressure had to just pick kalendae and try make it work without scheduler framework
Tech Stores:
Find, Learn, Test encryption for password | 7
Find, Learn, Test Graphing framework | 4

## Sprint 2018-03-04
User Stories | Story Points | Done
As a general user, I want my info to be secure. | 2 | As Admin I want to be able to edit the scheudule for all color rooms | 7
As a general user I want to be able to identify who is faciliatating for a shift. | 1 | As Board I want to be able to view the schedule | 1
|  | As Teacher I want to be able to view schedule from all color rooms | 1
Tech Stores: |  | As family I want to be able to edit my own schedule, delete or add. But only my accounts | 2
Find, Learn, Test encryption for password | 7 | As Family I want to be able to view how many hours I need to facilitate for. | 2
Find, Learn, Test Graphing framework | 4 | As a general user I want to be able to identify who is faciliatating for a shift. | 1
Finally learnt calendar framework and worked really hard. Very busy week.
Light work in background on security and graphing for stats

## Sprint 2018-03-11
User Stories | Story Points | Done
As a general user, I want my info to be secure. | 2 | As a general user I want to be able to identify who is faciliatating for a shift. | 1
|  | Find, Learn, Test encryption for password | 7
Tech Stores:
Find, Learn, Test Graphing framework | 4
Encryption is giving us a lot of trouble. Underestimated the time.
Also some time spent on graphing framework but not comfortable enough to put it on the "done"
Ahmad worked on statistical representation that was suppose to be for next sprint. Not neccesarily done so can not include into done category

## Sprint 2 Burndown Chart
| Week0 | Week1 | Week2 | Week3 | Week4
Actual Remaining Days | 36 | 34 | 28 | 14 | 6
Estimated Remaining Days | 36 | 27 | 18 | 9 | 0
Didn’t quite make it in the end. Calendar and Encryption gave us a lot more trouble than expected.
Couldn’t learn high charts well enough to add it to the "done" pile

## Sprint 2 Retrospective
Retrospective
Good
Got a lot of manhours in
Found a scheduling and date picker framework
Met our preset goals (almost)
Got over a lot of integration hiccups
Not so Good
Didn’t estimate how long it would take to learn a new technology and implement it
Did not account for difficulty in finding and testing new framework
More implementations exposed weak code structure
Overestimated our goals, did not finish sprint
Improvement
Better documentation, more descriptive
Focus on doing less but making it better
Estimate our goals better
More testing to ensure quality

## Sprint 3
User Stories | Story Points |  | Goals
As Admin I would like encrypted passwords for security | 7 | These 3 will be grouped together for story points | Basic level security for all users, password wise
As Board I would like encrypted passwords for security |  |  | Improved UI for family users
As Family I would like to know that my password is safe |  |  | Donating feature
As Family I would like to know how many hours I have facilitated | 2 |  | Increased shift slots
As Family I would like to know how many hours I need to facilitate | 1 |  | Overall testing
As Family I would like to know which shifts I have coming up | 1
As Family I would like to be able to donate shifts | 2
As Teacher I would like 3 or more facilitators per a shift | 3
Tech Stores:
Testing of 3 facilitator slots | 2
Testing of donating to Family | 1
Testing of donating back | 1
Testing of hour counting for current and needed | 1
Testing of upcoming shifts | 1
Testing for security | 4
Testing of overall program | 2
Total | 28
| Available Days | (4 week sprint)
Matthew | 9
Ahmad | 9
Lukas | 9
Raymond | 9
36 available man-days
Last Sprint's Focus Factor: 30 Story Points/ 38 man days = 0.78
Focus Factor: 0.78
This sprint's estimated velocity: 36 man days * 0.78 = 28 story points

## Sprint 2018-03-18
User Stories | Story Points | Done
As Admin I would like encrypted passwords for security | 7
As Board I would like encrypted passwords for security
As Family I would like to know that my password is safe |  | This week was primarily scheduled for Sprint 2 demo preparation. No work done on Sprint 3.
As Family I would like to know how many hours I have facilitated | 2
As Family I would like to know how many hours I need to facilitate | 1
As Family I would like to know which shifts I have coming up | 1
As Family I would like to be able to donate shifts | 2
As Teacher I would like 3 or more facilitators per a shift | 3
Tech Stores:
Testing of 3 facilitator slots | 2
Testing of donating to Family | 1
Testing of donating back | 1
Testing of hour counting for current and needed | 1
Testing of upcoming shifts | 1
Testing for security | 4
Testing of overall program | 3

## Sprint 2018-03-25
User Stories | Story Points | Done
As Family I would like to know how many hours I have facilitated | 2 | As Admin I would like encrypted passwords for security | 7
As Family I would like to know how many hours I need to facilitate | 1 | As Board I would like encrypted passwords for security
As Family I would like to know which shifts I have coming up | 1 | As Family I would like to know that my password is safe
As Family I would like to be able to donate shifts | 2 | As Teacher I would like 3 or more facilitators per a shift | 3
Tech Stores:
Testing of 3 facilitator slots | 2
Testing of donating to Family | 1
Testing of donating back | 1
Testing of hour counting for current and needed | 1
Testing of upcoming shifts | 1
Testing for security | 4
Testing of overall program | 3

## Sprint 2018-04-01
User Stories | Story Points | Done
As Family I would like to know which shifts I have coming up | 1 | Testing for security | 4
|  | Testing of 3 facilitator slots | 2
|  | As Family I would like to know how many hours I have facilitated | 2
Tech Stores: |  | As Family I would like to know how many hours I need to facilitate | 1
Testing of donating to Family | 1 | As Family I would like to be able to donate shifts | 2
Testing of donating back | 1
Testing of hour counting for current and needed | 1
Testing of upcoming shifts | 1
Testing of overall program | 3
Pretty busy week. Lots to implement and some testing.

## Sprint 2018-04-08
User Stories | Story Points | Done
|  | As Family I would like to know which shifts I have coming up | 1
|  | Testing of donating to Family | 1
|  | Testing of donating back | 1
Tech Stores: |  | Testing of hour counting for current and needed | 1
|  | Testing of upcoming shifts | 1
|  | Testing of overall program | 2
Finished everything and had some extra time to do further testing of program

## Sprint 3 Burndown Chart
| Week0 | Week1 | Week2 | Week3 | Week4
Actual Remaining Days | 28 | 28 | 18 | 7 | 0
Estimated Remaining Days | 28 | 21 | 14 | 7 | 0

## Sprint 3 Retrospective
Retrospective
Good
Have majority of user stories done
Good testing
Not so Good
Feeling burnt out
Weak first week of the sprint
Improvement
Start sprint 1 week later so data would not be skewed

## Karen meeting notes
Karen meeting:
Teachers who are also parents still have to put in the hours.
Keep it basic
Not eveyone who is a faciliator is also a parent ***
Doesnt want parents to create their own accounts
3 faciliator in each time block, but more than 3 people can sign up
Sign up time is static but if they can only come for a portion of time, should be able to do that.
A single family account for each family
At most 2 facilitator positions, either parents/board member or parent/teacher
Seperate account type if a parent and board member/teacher
Parents can access signup sheet schedule for the whole school year
Seperate login that is easily accessible *
Want the teachers to have no powers because they are union, just viewing powers
TA can only book hours